## TIMELINE
IT Product IntelliDART Development Implementation Timeline
Phase | Task / Subtask | Start Date | End Date | Notes / Description
Phase 1 | Requirement Gathering & Analysis | 2025-11-03 | 2025-12-15
| — Stakeholder Identification | 2025-11-03 | 2025-11-03 | Identify all internal/external stakeholders for inputs
| — Stakeholder Interviews | 2025-11-04 | 2025-11-10 | Schedule & conduct detailed interviews to gather needs
| — Market & Competitor Research | 2025-11-04 | 2025-11-12 | Analyze competitor products, market trends, gaps
| — User Persona Development | 2025-11-11 | 2025-11-14 | Define target user types with demographics, behaviors, goals
| — Requirement Documentation | 2025-11-15 | 2025-11-20 | Document functional & non-functional requirements
| — MVP Feature Prioritization | 2025-11-21 | 2025-11-25 | Use MoSCoW or other prioritization techniques
| — Scope & Constraints Definition | 2025-11-26 | 2025-12-01 | Define what’s in scope/out of scope, tech, timeline, resource limits
| — Requirement Review & Approval | 2025-12-02 | 2025-12-05 | Circulate for stakeholder feedback and approval
Phase 1 | Design & Prototyping | 2025-12-06 | 2026-01-31
| — Create Wireframes | 2025-12-06 | 2025-12-15 | Low fidelity sketches for key screens
| — User Flow Mapping | 2025-12-10 | 2025-12-18 | Map navigation paths & interactions
| — Design Mockups (High Fidelity) | 2025-12-16 | 2025-12-25 | Detailed UI design, branding
| — Interactive Prototype Development | 2025-12-26 | 2026-01-05 | Build clickable prototype
| — Usability Testing | 2026-01-06 | 2026-01-15 | Conduct testing sessions with sample users, collect feedback
| — Design Iterations | 2026-01-16 | 2026-01-25 | Refine designs based on usability feedback
| — Finalize Design System & Style Guide | 2026-01-26 | 2026-01-31 | Document UI components, typography, colors, guidelines
Phase 2 | Backend Core Development | 2026-02-01 | 2026-05-31
| — Design Database Schema | 2026-02-01 | 2026-02-10 | Define entities, relationships, normalization
| — Setup Development Environment | 2026-02-01 | 2026-02-05 | Configure servers, CI/CD pipelines, source control
| — Develop Authentication Module | 2026-02-06 | 2026-02-20 | Login, registration, password recovery
| — Develop Core APIs | 2026-02-21 | 2026-04-10 | CRUD operations, business logic
| — Implement Third-party Integrations | 2026-04-11 | 2026-04-25 | Payment gateways, analytics, email services
| — Unit Testing Backend Components | 2026-04-26 | 2026-05-05 | Write and run unit tests
| — Code Review & Refactoring | 2026-05-06 | 2026-05-15 | Ensure code quality, optimize performance
| — Backend Documentation | 2026-05-16 | 2026-05-31 | API docs, system architecture diagrams
Phase 2 | Frontend Core Development | 2026-02-01 | 2026-05-31
| — Setup Frontend Environment | 2026-02-01 | 2026-02-05 | Configure frameworks, linters, build tools
| — Develop Responsive Layouts | 2026-02-06 | 2026-03-10 | Mobile, tablet, desktop views
| — Implement UI Components | 2026-03-11 | 2026-04-15 | Buttons, forms, navigation menus, modals
| — Connect to Backend APIs | 2026-04-16 | 2026-05-10 | Data fetching, state management
| — Accessibility Compliance | 2026-05-01 | 2026-05-20 | WCAG standards adherence
| — Cross-browser & Device Testing | 2026-05-15 | 2026-05-25 | Ensure consistent behavior on all major browsers/devices
| — Unit Testing Frontend Components | 2026-05-20 | 2026-05-31 | Write and run tests
Phase 3 | Integration & Testing | 2026-06-01 | 2026-08-31
| — Integration Testing | 2026-06-01 | 2026-06-20 | Test end-to-end data flow between frontend & backend
| — Performance Testing | 2026-06-21 | 2026-07-10 | Load testing, stress testing, response times
| — Security Testing | 2026-07-11 | 2026-07-30 | Vulnerability scans, penetration tests
| — Bug Tracking & Fixing | 2026-07-15 | 2026-08-20 | Log bugs, prioritize fixes, implement patches
| — Regression Testing | 2026-08-10 | 2026-08-31 | Ensure fixes don’t break existing features
Phase 3 | MVP Launch Preparation | 2026-09-01 | 2026-10-15
| — Production Environment Setup | 2026-09-01 | 2026-09-10 | Setup servers, load balancers, backups
| — CI/CD Pipeline Finalization | 2026-09-05 | 2026-09-15 | Automate deployments
| — User Onboarding Content | 2026-09-16 | 2026-09-30 | Tutorials, FAQs, support docs
| — Support Team Training | 2026-10-01 | 2026-10-07 | Train helpdesk and customer support
| — Marketing & Launch Campaign Planning | 2026-09-20 | 2026-10-10 | Coordinate with marketing team
| — Monitoring & Alerting Setup | 2026-10-01 | 2026-10-15 | Configure logs, alerts for critical systems
Phase 3 | MVP Launch | 2026-10-16 | 2026-10-31
| — Production Deployment | 2026-10-16 | 2026-10-17 | Final push to production
| — System Monitoring | 2026-10-18 | 2026-10-31 | Real-time monitoring of system health
| — User Support & Issue Resolution | 2026-10-18 | 2026-10-31 | Provide support and patch urgent issues
| — Collect Initial User Feedback | 2026-10-20 | 2026-10-31 | Surveys, interviews, usage analytics
Phase 4 | User Feedback Collection & Analysis | 2026-11-01 | 2027-01-31
| — Survey Creation & Distribution | 2026-11-01 | 2026-11-15 | Design feedback surveys, distribute to users
| — User Interviews & Focus Groups | 2026-11-16 | 2026-12-15 | Conduct detailed feedback sessions
| — Data Analysis & Reporting | 2026-12-01 | 2027-01-10 | Analyze survey and usage data
| — Prioritize Improvements | 2027-01-11 | 2027-01-31 | Rank feedback items based on impact and feasibility
Phase 4 | Iterative Enhancements | 2027-02-01 | 2027-07-31
| — Bug Fix Implementation | 2027-02-01 | 2027-03-31 | Fix reported issues
| — UX/UI Improvements | 2027-04-01 | 2027-05-15 | Refine designs based on feedback
| — Minor Feature Development | 2027-05-16 | 2027-07-15 | Add small requested features
| — Continuous Testing & QA | 2027-02-01 | 2027-07-31 | Ongoing testing of new fixes/features
Phase 5 | Scalability & Performance Improvements | 2027-08-01 | 2028-01-31
| — Load & Stress Testing | 2027-08-01 | 2027-08-31 | Simulate peak loads
| — Database Optimization | 2027-09-01 | 2027-10-15 | Index tuning, query optimization
| — Implement Caching | 2027-10-16 | 2027-11-30 | Add Redis, CDN caching
| — Infrastructure Scaling | 2027-12-01 | 2028-01-15 | Add servers, auto-scaling
| — API Response Optimization | 2028-01-16 | 2028-01-31 | Refactor slow endpoints
Phase 6 | Security & Compliance Upgrades | 2028-02-01 | 2028-07-31
| — Penetration Testing | 2028-02-01 | 2028-03-15 | External security audit
| — Data Encryption Implementation | 2028-03-16 | 2028-04-30 | Encrypt data at rest and in transit
| — Compliance Documentation | 2028-05-01 | 2028-05-31 | GDPR, CCPA policies, user consent tracking
| — Security Policy Updates | 2028-06-01 | 2028-06-30 | Update internal security policies
| — Team Security Training | 2028-07-01 | 2028-07-31 | Train team on security best practices
Phase 7 | New Module Design & Development | 2028-08-01 | 2028-12-15
| — Requirement Gathering | 2028-08-01 | 2028-08-15 | Define scope for new modules
| — Architectural Design | 2028-08-16 | 2028-08-31 | Plan module integration